## Sponsor Inputs
# | High level ideas / Features
1 | Create Account
2 | View Restaurants
3 | Search Restaurants
4 | View Menu
5 | Add to Cart
6 | Purchase
7 | Restaurant views order
8 | Restaurant marks order as delivered
Notes:
1 | The above points were listed as draft ideas by the project sponsor.
2 | The project sponsor mentioned that he wants to compete against Talabat.
3 | As a sponsor, I am planning to compete against Talabat.
4 | This is a view only file, you can make a copy then edit in the copy.
5 | You can find a tab named Product Backlog Template, please feel free to use it when creating your product backlog.

## Product Backlog Template
# | Epic | User Story | Priority | Ready to be planned | Planned Sprint | Status
1 | Create Account | As a customer, I need to create account so that I can use the application | High | done | 1 | done
2 | Create Account | As a customer, I need to create account so that I can use my previouse logs and orders | High | done | 1 | done
3 | Create Account | As a product owner, Customer's accounts should be created so that I can track the progress | Medium | done | 1 | done
4 | Create Account | As a delivery man, I need to create account so that I get notified for each delivery | High | done | 1 | done
5 | Create Account | As a restaurant, I need to create account so that I can list my products and menu | High | done | 2 | done
6 | View Restaurants | As a customer, I need to view available restaurants so that I can choose the desired one | Medium | ready | 2 | plannig
7 | View Restaurants | As a delivery man, I need to vire restaurants location so that I prioritize my deliveries | High | ready | 2 | plannig
8 | Search Reastaurants | As a customer, I need to be able to search for a specific restaurant that I previously know | High | not ready | 3 | plannig
9 | View Menu | As a customer, I need to view restaurant's menus in order to choose what to order | High | not ready | 3 | plannig
10 | Add to Cart | As a customer, I need to add orders to my cart so that I can easilt order many orders from different restaurants | Low | not ready | 3 | plannig
11 | Purchase | As a customer, I need to be able to choose purchase option | High | not ready | 4 | plannig
12 | Purchase | As a restaurant, I need to get notified with a customer purchase so that I prepare the order | High | not ready | 4 | plannig
13 | Restaurant views order | As an employee, I need to view customers orders so that I can manage them | High | not ready | 5 | plannig
14 | Restaurant marks order as delivered | As a customer, I need to be notified when orders arrive so that I receive it or complain if it didn't accually arrive | Low | not ready | 5 | plannig