## Sheet1
| Unaware | Resistant | Neutral | Supportive | Leading | Purpose | Responsibility | Meduim | Content | Frequency
Customer ex. Amazon |  |  | C | D |  | Project Status SW Review Status | PM | Meeting | Demo Issues - Risks and Software Reviews | Bi-weekly
Team |  |  |  |  | C D | Team Status | PM | Meeting | Pace, Issues and Risks | Weekly
Sponsor |  | C |  |  | D | Project Review | PM | Meeting | Resources and Reviews | Weekly
Google | C |  |  | D |  | Authentication Status | PM | Meeting | Compatibility, Issues and Reviews | Bi-weekly
Banks | C |  | D |  |  | Customer Account Status | PM | Meeting | Compatibility, Digitalization Issues and Reviews | Monthly
Card Holder | C D |  |  |  |  | Review Errors | PM | E-mail | Reviews and Issues | Monthly